## 21 No. P.A. Form
FIRST & FINAL BILL
|  |  | યોજના: | ૧૫ મુ નાણાપંચ ગ્રામ્ય કક્ષા વર્ષ ૨૦૨૫-૨૬ પ્રથમ હપ્તો
નોંધ :- (જુઓ નિયમ - ૧૪૪)
પી.એ.ફોર્મ
પ્રથમ-છેવટનું બિલ
પેટા વિભાગ :- ના.કા.ઇ.શ્રી, મા. અને મ. (પં.) પેટા વિભાગ, |  |  | ડાકોર.
કામનું નામ :- | ભદ્રાસા તાબે નવાદાજીપુરામાં સી.સી. રસ્તાનું કામ. |  |  |  |  | તા. ઠાસરા | 12
કોન્ટ્રાક્ટર અથવા છુટક કામ કરનારનું નામ તથા સરનામું :- |  |  | સરપંચ શ્રી ગ્રામ પંચાયત |  |  | ભદ્રાસા | 20
|  | તાલુકા પંચાયત કચેરી | તા. ઠાસરા | ના હુકમ નંબર- | જા. નં. વિકાસ/વશી/૧૭૯૧. તા. ૨૩/૦૩/૨૦૨૬. |  | 8
માપ સામે તપાસ્યુ છે અને ખરૂ માલુમ પડયું છે. |  |  | એ માપો તપાસ્યા અને જોયું અને રૂ....................... /- |  |  |  | 26
|  |  | નું બિલ મંજુર કર્યુ. |  |  |  | 12
પે.વિ.અ.ના કારકુનની ટુંકી સહી |  |  | પે.વિ.અ.ના કારકુનની ટુંકી સહી
ઓવરશીયર |  |  | ઓવરશીયર
સહી તથા તારીખ |  |  | સહી તથા તારીખ
તપાસી જોયુ |  |  | મુખાલસી કરી
હિસાબ તપાસણી કરનાર કારકુનની ટુંકી સહી |  |  | એક્ઝીક્યુટીવ એન્જીનીઅર
બીલની રકમ મળી
તારીખ |  |  | તાલુકા /જીલ્લા/પંચાયત
નાણા મેળવનારની સહી અથવા અંગુઠાની છાપ
નાણાં લેનાર અભણ હોય તો
રૂ....................................) આપવા |  |  | સાક્ષીની સહી તથા તારીખ
તારીખ...................... ..... હિસાબનીશ
હિસાબનીશ |  |  | મંત્રી
તાલુકા/ જીલ્લા/પંચાયત |  |  | તાલુકા/ જીલ્લા/પંચાયત
.................................તારીખનો ચેક ક્રમાંક થી
ખાતે ઉધાર્યા. |  |  | પગાર કર્યા અને તે નાણાં
ખાતાવહી પાનું
વાઉચર ક્રમાંક
21

## Bill
ભદ્રાસા તાબે નવાદાજીપુરામાં સી.સી. રસ્તાનું કામ.
કામ અથવા માલની રકમ (અંદાજની પેટા સદરો પ્રમાણે સમુહમાં ગોઠવેલ) | આજ તારીખ સુધીનું પરીણામ | દર | દીઠ | આજ તારીખ સુધીની રકમ | આગલા બીલથી આજ તારીખ સુધીની રકમ | શેરો
ITEM NO 1 : Demolition including stacking of serviceable materilas and disposal of unserviceable materials with all lead and lift. (i) R.C.C. work | 0 | 1030.81 | Cu.m | 0
Item No :- 2 Excatation for pipe line trenches incl. all safety provision using site rails & stacking excavated stuff up to a lead of 90 M. cleaing the site etc. complete for lift & strata as specified.(A) in all sorts of soil and soft murrum (a) Upto 1.5 mt. depth | 205.33 | 89 | Cu.m | 18274.37
Item No :- 3 Providing & supplying ISI standard R.C.C. pipe (or Sulphate Resistance cement) in standard length of following class & diameter suitable for either collar joints or rubber ring joints including all taxes, insurance, transportation, freight charges, octroi, inspection charges,loading, unloading, conveyance to departmental stores, stacking etc. comp. ( IS - 458 / 1989 ) for following dia.d) Class NP2 Test Pressure, 0.7 Kg/sq.cm
(1) 225 mm. Dia R.C.C. Pipe | 0 | 421 | Rmt | 0
(2) 300 mm. Dia R.C.C. Pipe | 100 | 672 | Rmt | 67200
(3) 450 mm. Dia R.C.C. Pipe | 92.5 | 817 | Rmt | 75572.5
(4) 600 mm Dia R.C.C. Pipe | 70 | 1331 | Rmt | 93170
(5) 900 mm Dia. R.C.C. Pipe | 0 | 2476 | Rmt | 0
(6) 1200 mm Dia. R.C.C. Pipe | 0 | 4121 | Rmt | 0
Item No :- 4 Lowing laying & joining R.C.C. pipes in C.M. 1:1 1/2 of follwing diameter in proper position garde aligment as directed by Engg. Incl. Conveyance from store to site of work labour giving hydraulic testing as per ISI code etc. comple incl.
(1) 225 mm. Dia R.C.C. Pipe | 0 | 88 | Rmt | 0
(2) 300 mm. Dia R.C.C. Pipe | 100 | 119 | Rmt | 11900
(3) 450 mm. Dia R.C.C. Pipe | 92.5 | 171 | Rmt | 15817.5
(4) 600 mm Dia R.C.C. Pipe | 70 | 228 | Rmt | 15960
(5) 900 mm Dia. R.C.C. Pipe | 0 | 340 | Rmt | 0
(6) 1200 mm Dia. R.C.C. Pipe | 0 | 440 | Rmt | 0
Item No:- 5 Constructing of valve chambers in brick or bela stone masonary, locally available in C.M. 1:6. Foundation concrete 150 mm thick in C.C. 1:4:8 of trap metal size 25 mm to 40 mm thick, inside cement plater in C.M. 1:3 and cement pointing outside in C.M. 1:3 and top cover of precast RCC slab 100 mm thick (with key hole in two parts, each with handles or MS Bar etc. comp.e as given size) Upto 1 Mt. depth from G.L. to pipe invert level incl. complete civil works but excluding cost of excavation and refilling. With cast in situ RCC slab in one single piece with fixing of CI - MH Frame and cover (excl. cost of CI -MH Frame & cover) with 23 mm thick brick masonary wall in C.M. 1:6.
Chamber size: 0.60 m x 0.60 m and 1.0 mt deep | 0 | 5138 | no. | 0
Chamber size: 0.90 m x 0.90 m and 1.0 mt deep | 5 | 7343 | no. | 36715
Chamber size: 1.30 m x 0.90 m and 1.0 mt deep | 2 | 8882 | no. | 17764
Chamber size: 1.30 m x 1.30 m and 1.0 mt deep | 0 | 10698 | no. | 0
Item No :- 6 Reflling the pipeline trencher incl. ramming watering comsolidating disposial of surplus stuff as directed withing radius of 3 K.M. | 154.33 | 22 | Cu.m | 3395.26
Item No:- 7 R.C.C. precast M.H.Frame & Cover Manufacture, supply & Delivery at store or at site of work precast R.C.C. M.200 Frame & cover suitable to drainage M.H. and as per type design & Drawing including cost of reinforcement M.S.Angle or Flate, curring mold work etc. (A) Heavy Duty
(1) Frame suitable for 50 cm opening of M.H. | 7 | 1121 | no. | 7847
(2) Cover suitable for 50 cm opening of M.H. | 7 | 1173 | no. | 8211
Item No. 8 Providing and laying cement concrete 1:2:4 (1- Cement : 2- Coarse sand : 4- graded stone aggregates 20 mm nominal size) and curing complete excluding cost of formwork in (A) Foundation and Plinth | 0 | 3652.31 | Cmt | 0
Item No. 9 Providing and fixing Number plate of marble stone of requiered size set in C.M. 1:4 etc. comp. | 1 | 306.14 | no. | 306.14
Total |  |  | Rs. | 372132.77
ADD 18% GST |  |  | Rs. | 66983.8986
Total |  |  | Rs. | 439116.6686
આપવાની ચોખ્ખી રકમ |  |  | Rs. | 439116
શ્રી- વી.એ.ઠાકોર | અ.મ.ઇ એ માપ લીધા અને નીચે જણાવેલ માપપોથી નંબર તથા પાના નંબર ઉપર તે નોંધ્યા.
માપ નોંધ્યા તારીખ - | 11-05-2026.
MB NO - | 275 | PAGE NO | 14 | TO | 15
બીલ સ્વીકાર્યાના પ્રતિકરૂપે કોન્ટ્રાક્ટર અથવા છુટક કામ કરનારની સહી તથા તારીખ
અ.મ.ઇ શ્રી ની સહી

## COMP-14MU NAN
COMPLETION CERTIFICATE
GRANT | :- | ૧૫ મુ નાણાપંચ ગ્રામ્ય કક્ષા વર્ષ ૨૦૨૫-૨૬ પ્રથમ હપ્તો
NAME OF WORK | :- | ભદ્રાસા તાબે નવાદાજીપુરામાં સી.સી. રસ્તાનું કામ.
DETAILS OF T.S. | :- | 1701,03-26.
AMOUNT OF T.S. | :- | 379000
DETAILS OF A.S. | :- | તાલુકા પંચાયત કચેરી ઠાસરા ના હુકમ નંબર- જા. નં. વિકાસ/વશી/૧૭૯૧. તા. ૨૩/૦૩/૨૦૨૬.
AMOUNT OF A.S. | :- | 379000
NAME OF AGENCY | :- | સરપંચ શ્રી ગ્રામ પંચાયત |  |  | ભદ્રાસા
DATE OF STARTING | :- | 04-05-2026.
DATE OF COMPLETION | :- | 11-05-2026.
ACTUAL EXPENDITURE INCURED | :- | 439116
FINAL MEASUREMENT RECORDED IN | :- | MB NO - | 275 | PAGE NO | 14 | TO | 15
SHORT NOTED | :- | WORK IS COMPLETED.
Add.Ass.Engineer
TALUKA PANCHAYAT
તા. ઠાસરા