## Estimate
ESTIMATE
1. Division |  |  | R & B (P) DIV. | NADIAD | JILLA PANCHAYAT |  | NADIAD
2. Sub-Division |  |  | R & B (P) SUB DIV. | NADIAD | NANI SINCHAI (P) SUB DIV |  | NADIAD
|  |  | DEE ATVT PRANT | NADIAD
3. Sanctioned Estimate No:
4. Fund Head: |  |  | ૧૫ % વિવેકાધીન વર્ષ ૨૦૨૬-૨૭.
5. Major Head:
6. Minor Head:
7. Serviceable Head:
8. Departmental Head:
Estimated framed in the office of the Taluka Development Officer, Taluka Panchyat, | [5 empty] | VASO
for the expenses that will be incurred in the Work Of
કામ નું નામ :- |  | વસો ગામે ગામની મુખ્ય પાણી ની પાઈપ લાઇનનું કામ.
Amounting to Rs. |  |  |  |  | 100000
Administrative approval No.:
Date :
& Technically sanctioned under No.:
Date:
Estimate prepared by |  | : | Shree A.G.SUTHAR. A.A.E.
Estimate checked by: |  | : | Shree A.G.SUTHAR. A.A.E.
Call or Authority:
સામાન્ય વર્ણન અને સૈદ્ધાંતિક મંજૂરીની વિગતો.
SR. NO. | 18 | જા.નંબર/વશી- તા. /૦૩/૨૦૨૬.
આ કામ ઉપરોક્ત યોજના હેઠળ મંજૂર થયેલ છે. જે અનવયે સ્થળ સ્થિતિની તપાસ કરીને ગુ. પા. પૂ. અને ગટર વ્યવસ્થા બોર્ડ તેમજ મા. અને મ. વિભાગના પ્રવર્તમાન S.O.R. ના ભાવો મુજબ અંદાજપત્ર તૈયાર કરવામાં આવેલ છે. આ કમના નકશા-અંદાજમાં સ્થળ સ્થિતિ મુજબ ખોદાણ , પાઇપ પ્રોવાઈડ કરી ને ઉતારવી , ચેમ્બર , ફ્રેમ , કવર સાથે તથા તકતીની આઈટમનો સમાવેશ કરેલ છે.
ADD. ASST. ENGINEER
TALUKA PANCHAYAT
VASO

## Abstract
ABSTRACT SHEET
કામ નું નામ :- |  | વસો ગામે ગામની મુખ્ય પાણી ની પાઈપ લાઇનનું કામ.
QTY. | UNIT | ITEM | RATE INCL.1% LABOUR CESS | PER | AMOUNT
0 | Smt | ITEM NO 1 : Dismantling the exsting surface incl. disposing off the dismentalled material and stacking the useful materials directed | 202.2 | Smt | 0
1020.6
149.85 | Cum | Item No-2 Excavation for pipe line trenches including all safty provision using site rails stacking excavated stuff up to lead 90mt.clearing the site etc.complete. For lift & strata as specified.(a) in all sort of soil & soft murrum up to 1.5mt. Depth. | 89 | Cum | 13336.65 | 10.206
|  | (S.O.R.GWSB P.NO.40 / I.NO.15 ) |  |  |  | 1030.806
Item No-3 Providing & Supplying standard length ISI Mark regid unplastisied PVC Pipe suitable for potable water with ringfit joint inclunding cost of rings, as per IS specification no. 4985/1988 inclunding all local and central taxes, transportation, frelenght charges, octrol, inspection charges, loading unloading, conveyance to the departmental store and including cost of jointing meterial etc. complate. ( with Excise Duty)
(S.O.R.GWSB P.NO.17 / I.NO.1-B)
0 | Rmt | (1) 63 mm 6 kg / cm2 | 69 | Rmt | 0
0 | Rmt | (2) 75 mm 6 kg / cm2 | 96 | Rmt | 0
200 | Rmt | (3) 90 mm 6 kg / cm2 | 139 | Rmt | 27800
170 | Rmt | (4) 110 mm 6 kg / cm2 | 199 | Rmt | 33830
Item No-4 Lowering ,Laying & Jointing PVC pipes & specials including cost of conveyance from store to site of work including cost of labour, material except cost of cement ,solvent giving satisfactory hydraulic testing as per IS code.
G.W.S.S.B.S.O.R. P:- 39 Sec 1&2 (B) I.No. 11.b
0 | Rmt | (1) 63 mm 6 kg / cm2 | 12 | Rmt | 0
0 | Rmt | (2) 75 mm 6 kg / cm2 | 15 | Rmt | 0
200 | Rmt | (3) 90 mm 6 kg / cm2 | 17 | Rmt | 3400
170 | Rmt | (4) 110 mm 6 kg / cm2 | 19 | Rmt | 3230
146.9636 | Cmt | Item No-5 Refilling the pipe line trenches including ramming watering consolidating disposal of surplus stuff as directed within radius of 3.00 km. | 22 | Cmt | 3233.19
|  | (S.O.R.GWSB P.NO.41 / I.NO.10) | 22
1 | No | Item No-6 Providing and fixing Number plate of marble stone of requiered size set in C.M. 1:4 inch finishing & engraving letters etc comp. | 306.14 | No | 306.14
( R & B Sor P. 130 C No 26087 + 1% labour cess = 303.11+3.03=306.14)
Total |  |  |  |  | 85135.98
Add 18% GST |  |  |  |  | 15324.4764
Total |  |  |  |  | 100460.4564
Say Rs. |  |  |  |  | 100000
A.A.E.
Taluka Panchayat
VASO

## Measurement
MEASUREMENT SHEET
કામ નું નામ :- |  | વસો ગામે ગામની મુખ્ય પાણી ની પાઈપ લાઇનનું કામ.
|  | No | x | L | x | W | x | D | =
ITEM NO 1 : Dismantling the exsting surface incl. disposing off the dismentalled material and stacking the useful materials directed
|  | 1 | x | 0 | x | 0.45 |  |  | = | 0
[6 empty] | Total Qty |  |  | = | 0 | Smt
Item No-2 Excavation for pipe line trenches including all safty provision using site rails stacking excavated stuff up to lead 90mt.clearing the site etc.complete. For lift & strata as specified.(a) in all sort of soil & soft murrum up to 1.5mt. Depth.
| (1) 63 mm dia. | 1 | X | 0 | X | 0.45 | X | 0.9 | = | 0 | Cmt
| (2) 75 mm dia. | 1 | X | 0 | X | 0.45 | X | 0.9 | = | 0 | "
| (3) 90 mm dia. | 1 | X | 200 | X | 0.45 | X | 0.9 | = | 81 | "
| (4) 110 mm dia. | 1 | X | 170 | X | 0.45 | X | 0.9 | = | 68.85 | "
[6 empty] | Total Qty |  |  | = | 149.85 | Cmt
[6 empty] | Say |  |  | = | 149.85 | Cmt
Item No-3 Providing & Supplying standard length ISI Mark regid unplastisied PVC Pipe suitable for potable water with ringfit joint inclunding cost of rings, as per IS specification no. 4985/1988 inclunding all local and central taxes, transportation, frelenght charges, octrol, inspection charges, loading unloading, conveyance to the departmental store and including cost of jointing meterial etc. complate. ( with Excise Duty)
| (1) 63 mm dia. | 1 | X | 0 |  |  |  |  | = | 0 | Rmt.
| (2) 75 mm dia. | 1 | X | 0 |  |  |  |  | = | 0 | Rmt.
| (3) 90 mm dia. | 1 | X | 200 |  |  |  |  | = | 200 | Rmt.
| (4) 110 mm dia. | 1 | X | 170 |  |  |  |  | = | 170 | Rmt.
Item No-4 Lowering ,Laying & Jointing PVC pipes & specials including cost of conveyance from store to site of work including cost of labour, material except cost of cement ,solvent giving satisfactory hydraulic testing as per IS code.
| (1) 63 mm dia. | 1 | X | 0 |  |  |  |  | = | 0 | Rmt.
| (2) 75 mm dia. | 1 | X | 0 |  |  |  |  | = | 0 | Rmt.
| (3) 90 mm dia. | 1 | X | 200 |  |  |  |  | = | 200 | Rmt.
| (4) 110 mm dia. | 1 | X | 170 |  |  |  |  | = | 170 | Rmt.
Item No-5 Refilling the pipe line trenches including ramming watering consolidating disposal of surplus stuff as directed within radius of 3.00 km.
| Deduction |  |  |  |  | Excavated Qty. |  |  | = | 149.85 | Cmt.
| (1) 63 mm dia. | 0.785 | X | 0.065 | X | 0.065 | X | 0 | = | 0 | Cmt
| (2) 75 mm dia. | 0.785 | X | 0.075 | X | 0.075 | X | 0 | = | 0 | Cmt
| (3) 90 mm dia. | 0.785 | X | 0.09 | X | 0.09 | X | 200 | = | 1.2717 | Cmt
| (4) 110 mm dia. | 0.785 | X | 0.11 | X | 0.11 | X | 170 | = | 1.6147 | Cmt
[6 empty] | Total Qty |  |  | = | 2.8864 | Cmt
[6 empty] | Net Qty |  |  | = | 146.9636 | Cmt.
[8 empty] | Say | = | 146.9636 | Cmt.
Item No-6 Providing and fixing Number plate of marble stone of requiered size set in C.M. 1:4 inch finishing & engraving letters etc comp.
|  | 1 | x | 1 |  |  |  |  | = | 1 | No
[6 empty] | Total Qty |  |  | = | 1 | No

## TEST-SITE
કામ નું નામ :- | વસો ગામે ગામની મુખ્ય પાણી ની પાઈપ લાઇનનું કામ.
SCHEUDULE OF TESTING
Sr. No | Item | No of testing required |  | Approved Rate |  | Amount
1 | Bricks | 0 | x | 578 | = | 0
2 | Sand | 0 | x | 388 | = | 0
3 | Cement | 0 | x | 788 | = | 0
4 | Cube | 0 | x | 238 | = | 0
5 | B.T.Kapchi | 0 | x | 546 | = | 0
6 | Metal | 0 | x | 696 | = | 0
7 | Paving Blocks | 0 | x | 220 | = | 0
8 | Steel | 0 | x | 294 | = | 0
9 | Pipe Line | 0 | x | 300 | = | 0
10 | Gutter Pipe | 1 | x | 300 | = | 300
300
SITE PLAN
A.A.E.
TALUKA PANCHAYAT
VASO